GOVERNMENT OF PAKISTAN

Ministry of Energy (Power Division)

TERMS OF REFERENCE

Advertising Agency (Traditional Media)

Power Subsidy Reform — National CNIC-to-Meter Linkage Campaign

# A. Background

The Government of Pakistan, through the Ministry of Energy (Power Division), is implementing a major structural reform of its electricity subsidy framework, moving from the existing broad-based, consumption-linked tariff differential subsidy to a new targeted electricity subsidy programme. Eligibility for the new programme will be determined through an income/socio-economic verification process, with beneficiary identification leveraging the National Socio-Economic Registry (NSER) database maintained by BISP.

The critical technical enabler of this reform is the linkage of electricity meters to consumers' Computerised National Identity Cards (CNICs). Once a consumer's CNIC is linked to their meter in the relevant Distribution Company (DISCO) database, the system will be able to identify eligible households and apply the appropriate subsidy directly to their monthly electricity bill. As a broader national goal, the Power Division envisions that all electricity consumers in Pakistan will eventually have their CNICs linked to their meters, creating a data-driven foundation for future energy policy.

To drive public awareness and ensure nationwide compliance, the Power Division is separately engaging three specialised communications each through an independent, single-consultant selection process under the World Bank Procurement Regulations for IPF Borrowers, submitted as three separate activities on the Bank's STEP system. All three firms will work in close coordination under the oversight of the Power Division (Section E). This Terms of Reference covers the Advertising Agency (Traditional Media) only.

# B. Communication Objectives and Core Messaging

### The overarching objective of the campaign is to help all audiences understand: (i) how the new targeted subsidy mechanism works; (ii) what consumers need to do to access it, including CNIC-to-meter linkage and NSER registration; (iii) what the reform means for their electricity bill; and (iv) how to raise a query or complaint through the grievance redress mechanism. The consultant will ,assist the Power Division in recording, tracking, and responding to complaints received..

### The Firm shall assist the Power Division in recording, tracking, and responding to queries and complaints received through digital and social media channels, and in feeding these into the Power Division's formal Grievance Redress Mechanism (GRM), consistent with the reporting requirements at Section 3.

### The Firm shall work from a single, Power Division-approved Messaging Bible, developed collaboratively across all firms — with the PR & Media Relations Firm in the lead advisory role — and approved by Power Division before any public-facing content is produced. All creative and public-facing materials require prior written Power Division approval; departure from the approved messaging framework is grounds for contract termination.

### Illustrative Messaging Themes

- What the reform is: a new, targeted electricity subsidy for verified low-income households, replacing the current broad-based subsidy. The reform is needed to ensure that limited public resources are directed more effectively to households that need electricity subsidy support, while improving the targeting, transparency, and sustainability of the subsidy system.

- What consumers need to do: link their CNIC to their electricity meter; if not already registered, register with NSER.

- What it means for their bill: The Firm shall assist the Power Division in communicating impacts of the policy changes to all customer categories and, where required, to individual customers based on the impact assessment study currently being finalized by the Power Division.

- Where to get help: a defined grievance redress channel — helpline, portal, and/or DISCO counter [channel to be specified].

Messaging must be tailored to each of the two campaign phases (Section D) and must speak to all electricity consumers, not only BISP beneficiaries (Section E.4).

# C. Campaign Phasing and Timeline

The assignment runs from onboarding in October 2026, with work starting on or before November 2026, through to campaign close in April 2027.

Phase 1 — Consumer Registration & Readiness (November 2026 – January 2027): focuses on CNIC-to-meter linkage and NSER registration for eligible households not already registered.

Phase 2 — Subsidy Programme Rollout (February – April 2027): focuses on enrolment procedures, meter linking/delinking processes, the grievance redress mechanism, and other operational aspects required for beneficiaries to access support, including public awareness and beneficiary onboarding.

# D. Institutional Arrangements

### D.1 Reporting

The Firm shall report directly to the PIU PD at Ministry of Energy Power Division. All deliverables, reports, and communications must be addressed to this focal point unless otherwise specified in writing.

### D.2 Coordination and Dedicated Government Team

Power Division shall designate a dedicated subsidy-reform communications team within the Power Division/Ministry of Energy — composition and focal person to be notified at contract signing — responsible for overall campaign direction and for coordinating among the three firms engaged under the campaign. Day-to-day advisory input on public response and messaging strategy is led by the PR & Media Relations Firm, subject to Power Division approval.

The Firm shall participate in fortnightly joint coordination meetings, alongside the other  firms engaged under the campaign, chaired by the Power Division focal person, and shall nominate a designated coordination point for inter-firm communication. All three firms must adhere to the shared Messaging Bible; in the event of any messaging conflict, the Power Division's decision is final and binding.

The scope of services includes support for stakeholder engagement and coordination with key institutions involved in the reform — particularly Power Division, BISP, and the DISCOs — and other relevant Government entities, as directed by the Power Division focal person.

### D.3 Approvals

All creative materials, media plans, press releases, digital content, and any other public-facing outputs must receive prior written approval from the Power Division before production, release, or placement. The Power Division shall provide feedback within five (5) working days of submission.

### D.4 Target Audience

Given the objective of establishing a nationwide CNIC-to-meter linkage system and preparing for the broader targeted subsidy framework, campaign materials shall be designed to reach all electricity consumers, with tailored messaging for specific beneficiary groups (e.g., NSER-registered households) where needed. No deliverable, target audience, or message shall be framed exclusively around BISP beneficiaries.

## 2. Scope of Services

The Agency is responsible for all traditional paid-media production and placement activities across both phases, including broadcast, print. Paid digital and social media advertising is outside this scope and falls under the separate Digital & Social Media Solutions Firm assignment.

### 2.1 Phase 1 Deliverables (November 2026 – January 2027)

- Television Commercials (TVCs): design, production, and placement in Urdu and regional languages (Punjabi, Sindhi, Pashto, Balochi, Seraiki) on national and provincial broadcasters.

- Radio Spots: production and placement in Urdu and regional languages on national and provincial stations.

- Print Advertisements: design, production, and placement in regional newspapers across all DISCO regions.

### 2.2 Phase 2 Deliverables (February – April 2027)

- Television Commercials (TVCs): national campaign in Urdu and regional languages with broader reach and updated general-consumer messaging.

- Radio Spots: national campaign with expanded coverage.

- Print Advertisements: national newspaper placement.

## 3. Deliverables and Reporting

- Monthly progress reports by the 5th of each following month, covering placements, reach data, and production status.

- Proof of Placement (PoP) for all paid traditional media.

- Mid-campaign evaluation report at the midpoint of each phase.

- Final Evaluation Report at the conclusion of each phase.

## 4. Minimum Qualification Requirements (Firm)

### 4.1 Minimum Experience

- Minimum five (5) years' continuous documented experience in advertising, media production, or campaign management:

- Minimum two (2) large-scale advertising campaigns for a federal/provincial government entity, SOE, or multilateral/bilateral organization — at least one nationwide: Signed completion certificate or satisfactory-performance letter.

### 4.4 No Conflict of Interest

- The Firm, its Key Experts, and any subcontractors shall not have existing contractual relationship with any DISCO, BISP, or entity directly involved in the Power Subsidy Reform: Signed conflict-of-interest declaration on firm letterhead.

## 5. Key Expert / Team Requirements

- Campaign Director / Team Lead: Master's degree in Marketing, Communications, or related field. Minimum 10 years leading advertising or integrated media campaigns; led at least two large-scale government or social-sector campaigns.

- Creative Director: Degree in Design, Mass Communication, or related field. Minimum 7 years in creative direction; portfolio demonstrating multilingual, multi-format work for mass audiences, low-literacy/rural experience preferred.

- Media Planning & Buying Specialist: Minimum 7 years in media planning and buying across TV, radio, print, and OOH; nationwide-campaign experience in Pakistan; familiarity with audience measurement tools.

- Power Sector Specialist: Minimum 5 years' professional experience in the power/energy/utilities sector; familiarity with DISCO operations, billing systems, and the regulatory environment.

- BISP / Social Protection Specialist: Minimum 5 years' experience working with or on behalf of BISP or social-protection programmes in Pakistan.

- SMS & Bill-Messaging Specialist: Minimum 5 years managing SMS campaign platforms, bulk SMS delivery, and performance tracking. (Paid digital/social platforms fall under the separate Digital & Social Media Solutions Firm assignment.

- Monitoring & Evaluation Officer: Minimum 5 years' M&E experience, including consumer awareness surveys; quantitative and qualitative analysis.

- Regional Language Content Specialists (minimum 3): Demonstrated proficiency and creative writing capability across a minimum of three distinct regional languages.

6. Selection Method.

Bidding would be conducted through Consultants Qualification based Selection (CQS) using a Request Expression of Interest (REOI) as specified in the World Bank’s “Procurement Regulations IPF Borrowers” dated Feb, 2025 “Procurement Regulations “and is open to all eligible firms as defined in the Procurement Regulations.

7. Estimated Volume of Work

| Sr no. | Deliverable | Total | Phase 1 Indicative Volume | Phase 2 Indicative Volume |
| --- | --- | --- | --- | --- |
| 01 | Television Commercials (TVCs) | 274 Spots | 137 | 137 |
| 02 | Radio Spots | 260 Spots | 130 | 130 |
| 03 | Print Advertisements | 33 Advertisement | 12 | 11 |

--- End of Terms of Reference ---